## User Stories
Epic | Epic | User Stories | Team Notes / Assumptions | Priority (1,2,3) | Release | Design | BE | FE | Mobile | DevOps | QA
Infrastructure/Setup | Infrastructure/Setup | Setup a hosting environment for STAGING |  | 1 | MVP
| Infrastructure/Setup | Setup a hosting environment for PROD |  | 1 | MVP
| Infrastructure/Setup | Setup Firebase authentication for LOCAL/STAGING/PROD |  | 1 | MVP
| Infrastructure/Setup | Install SSL Certs |  | 1 | MVP
| Infrastructure/Setup | Have a domain URL for the application |  | 1 | MVP
| Infrastructure/Setup | Have a system accessible email address |  | 1 | MVP
| Infrastructure/Setup | Have a code repository |  | 1 | MVP
| Infrastructure/Setup | Have a CI / CD pipeline |  | 1 | MVP
| Infrastructure/Setup | Have Log Aggregation |  | 1 | MVP
| Infrastructure/Setup | Have server / system error monitoring |  | 1 | MVP
| Infrastructure/Setup | Have Transaction Tracing |  | 1 | MVP
| Infrastructure/Setup | Create Graphql Server |  | 1 | MVP
Design Setup | Design Setup | Responsive Design (Interaction framework) for Chexer mobile app |  | 1 | R2
| Design Setup | Visual Approach and digital brand development |  | 1 | R2
| Design Setup | Isometric illustrations |  | 1 | R2
| Design Setup | Design Specifications and Asset supply |  | 1 | R2
| Design Setup | Edge cases (documented or designed) |  | 1 | R2
Design Admin Panel | Design Admin Panel | Admin Wireframes |  | 2 | R2
| Design Admin Panel | Admin Visual Design |  | 2 | R2
| Design Admin Panel | Admin Sitemap |  | 2 | R2
Merchant APIs |  | Authenticate Merchant |  | 1 | MVP
|  | Sent receipt info |  | 1 | MVP
Bank APIs |  | Authenticate Bank |  | 1 | MVP
|  | Send customer list |  | 1 | MVP
|  | Send card payment |  | 1 | MVP
|  | Receive receipt |  | 1 | MVP
Bankend actions |  | Save received receipt from merchant |  | 1 | MVP
|  | Save received card payment from bank |  | 1 | MVP
|  | Match merchant and bank info |  | 1 | MVP

## Estimate Summary - by Priority (hidden)
Overhead % | Contingency % | [5 empty] | QA %
#REF! | #REF! | [5 empty] | #REF!
Priority: | 1
Raw |  | Design Raw (hours) | Backend Raw (hours) | Frontend Raw (hours) | Mobile Raw (hours) | DevOps Raw (hours) | QA (hours)
|  | 0 | 0 | 0 | 0 | 0 | 0
Overhead | Meetings, Conversations, Feedback/Revisions, Unit Testing | Design with Overhead (hours) | Backend with Overhead (hours) | Frontend with Overhead (hours) | Mobile with Overhead (hours) | DevOps with Overhead (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Contingency | Unknowns, Risks | Design with Contingency (hours) | Backend with Contingency (hours) | Frontend with Contingency (hours) | Mobile with Contingency (hours) | DevOps with Contingency (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total hours |  | Design Total (hours) | Backend Total (hours) | Frontend Total (hours) | Mobile Total (hours) | DevOps Total (hours) | QA Total (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Hours per week | 20 | 40 | 40 | 40 | 40 | 20 | 20
Total weeks | PM Total (wks) | Design Total (wks) | Backend Total (wks) | Frontend Total (wks) | Mobile Total (wks) | DevOps Total (wks) | QA Total (wks)
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Staffing Plan (weeks) | 13 | 7 | 13 | 13 | 0 | 8 | 7
| weeks part-time | weeks full-time | weeks full-time | weeks full-time | weeks full-time | weeks part-time | weeks part-time
Priority: | 2
Raw |  | Design Raw (hours) | Backend Raw (hours) | Frontend Raw (hours) | Mobile Raw (hours) | DevOps Raw (hours) | QA (hours)
|  | 0 | 0 | 0 | 0 | 0 | 0
Overhead | Meetings, Conversations, Feedback/Revisions, Unit Testing | Design with Overhead (hours) | Backend with Overhead (hours) | Frontend with Overhead (hours) | Mobile with Overhead (hours) | DevOps with Overhead (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Contingency | Unknowns, Risks | Design with Contingency (hours) | Backend with Contingency (hours) | Frontend with Contingency (hours) | Mobile with Contingency (hours) | DevOps with Contingency (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total hours |  | Design Total (hours) | Backend Total (hours) | Frontend Total (hours) | Mobile Total (hours) | DevOps Total (hours) | QA Total (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Hours per week | 20 | 40 | 40 | 40 | 40 | 20 | 20
Total weeks | PM Total (wks) | Design Total (wks) | Backend Total (wks) | Frontend Total (wks) | Mobile Total (wks) | DevOps Total (wks) | QA Total (wks)
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Staffing Plan (weeks) | 2 | 2 | 0 | 0 | 0 | 0 | 0
| weeks part-time | weeks full-time | weeks full-time | weeks full-time | weeks full-time | weeks part-time | weeks part-time
Priority: | 3
Raw |  | Design Raw (hours) | Backend Raw (hours) | Frontend Raw (hours) | Mobile Raw (hours) | DevOps Raw (hours) | QA (hours)
|  | 0 | 0 | 0 | 0 | 0 | 0
Overhead | Meetings, Conversations, Feedback/Revisions, Unit Testing | Design with Overhead (hours) | Backend with Overhead (hours) | Frontend with Overhead (hours) | Mobile with Overhead (hours) | DevOps with Overhead (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Contingency | Unknowns, Risks | Design with Contingency (hours) | Backend with Contingency (hours) | Frontend with Contingency (hours) | Mobile with Contingency (hours) | DevOps with Contingency (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total hours |  | Design Total (hours) | Backend Total (hours) | Frontend Total (hours) | Mobile Total (hours) | DevOps Total (hours) | QA Total (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Hours per week | 20 | 40 | 40 | 40 | 40 | 20 | 20
Total weeks | PM Total (wks) | Design Total (wks) | Backend Total (wks) | Frontend Total (wks) | Mobile Total (wks) | DevOps Total (wks) | QA Total (wks)
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Staffing Plan (weeks) | 2 | 2 | 0 | 0 | 0 | 0 | 0
| weeks part-time | weeks full-time | weeks full-time | weeks full-time | weeks full-time | weeks part-time | weeks part-time
Priority:
Raw |  | Design Raw (hours) | Backend Raw (hours) | Frontend Raw (hours) | Mobile Raw (hours) | DevOps Raw (hours) | QA (hours)
|  | 0 | 0 | 0 | 0 | 0 | 0
Overhead | Meetings, Conversations, Feedback/Revisions, Unit Testing | Design with Overhead (hours) | Backend with Overhead (hours) | Frontend with Overhead (hours) | Mobile with Overhead (hours) | DevOps with Overhead (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Contingency | Unknowns, Risks | Design with Contingency (hours) | Backend with Contingency (hours) | Frontend with Contingency (hours) | Mobile with Contingency (hours) | DevOps with Contingency (hours) | QA (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total hours |  | Design Total (hours) | Backend Total (hours) | Frontend Total (hours) | Mobile Total (hours) | DevOps Total (hours) | QA Total (hours)
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Hours per week | 20 | 40 | 40 | 40 | 40 | 20 | 20
Total weeks | PM Total (wks) | Design Total (wks) | Backend Total (wks) | Frontend Total (wks) | Mobile Total (wks) | DevOps Total (wks) | QA Total (wks)
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Staffing Plan (weeks) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| weeks part-time | weeks full-time | weeks full-time | weeks full-time | weeks full-time | weeks part-time | weeks part-time